## 总览
PianoGrid Chords｜原规划 · 当前实现 · 完成目标
2026-09-13｜数量不代表用户任务完成；本表不证明代码、部署或SEO已验收。
口径 | 数量 | 依据与说明
原全站规划 | 127 | 原127完整保留，不作为当前发布数
原和弦核心＋共享支持 | 15 | 原13核心＋Guide／Finger Numbers
当前Chords系统 | 158 | 按历次包与用户报告重建
其中详情 | 145 | 基础25＋N2B48＋N2C48＋N2D24
其中分类 | 7 | Major／Minor／Dim／Aug／Sus／Seventh／Add
其中支撑 | 6 | Hub、By-key、Finder、Progressions、Guide、Finger
相对原核心新增 | 143 | 后续批准的新URL，不冒充原关键词需求
本包新增URL | 2 | Extended、Altered；不新增对象详情页
目标Chords系统 | 160 | 无其他并行模块变更时
当前全站业务URL（用户报告） | 171 | 未独立核对线上部署
目标全站业务URL | 173 | 假设其他模块本轮数量不变
框架输出（用户报告） | 5 | 代码build清单需在仓库确认
目标build输出 | 178 | 仅条件估算，不强制凑数
原任务组 | 38 | 按15个比较范围页逐组保留
原关键词记录 | 191 | 逐词原量/来源保留；未重查当前volume
下一步：让Codex执行 08_codex/00_一次执行到工程收尾.md；A–F连续推进，人工与真实SEO结果单独验收。

## 当前158路由
当前158路由
证据口径：原规划来自附件；实现来自用户报告，待Codex以同一版本核对；预测数量不作强制指标。
URL | 类型 | 批次 | 属于原127 | 原ID | 原代表词 | 原US量 | 实现证据 | 部署证据 | 动作
/chord-progressions | support | original15 | TRUE | U087 | piano chord progressions | 1600 | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords | support | original15 | TRUE | U075 | piano chord chart | 6600 | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/a-7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/a-add9 | detail | N2D_v2 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/a-augmented | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/a-diminished | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/a-flat-7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/a-flat-add9 | detail | N2D_v2 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/a-flat-augmented | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/a-flat-diminished | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/a-flat-m7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/a-flat-m7-flat5 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/a-flat-madd9 | detail | N2D_v2 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/a-flat-maj7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/a-flat-major | detail | original15 | TRUE | U079 | a flat chord piano | 1000 | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/a-flat-sus2 | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/a-flat-sus4 | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/a-m7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/a-m7-flat5 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/a-madd9 | detail | N2D_v2 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/a-maj7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/a-major | detail | original15 | TRUE | U076 | a chord piano | 4400 | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/a-minor | detail | original15 | TRUE | U078 | am piano chord | 1900 | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/a-sus2 | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/a-sus4 | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/add | category | N2D_v2 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/augmented | category | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/b-7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/b-add9 | detail | N2D_v2 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/b-augmented | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/b-diminished | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/b-flat-7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/b-flat-add9 | detail | N2D_v2 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/b-flat-augmented | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/b-flat-diminished | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/b-flat-m7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/b-flat-m7-flat5 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/b-flat-madd9 | detail | N2D_v2 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/b-flat-maj7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/b-flat-major | detail | N1 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/b-flat-minor | detail | N1 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/b-flat-sus2 | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/b-flat-sus4 | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/b-m7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/b-m7-flat5 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/b-madd9 | detail | N2D_v2 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/b-maj7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/b-major | detail | original15 | TRUE | U077 | b chord piano | 3600 | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/b-minor | detail | N1 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/b-sus2 | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/b-sus4 | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/by-key | support | original15 | TRUE | U085 | chords of key | 1900 | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/c-7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/c-add9 | detail | N2D_v2 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/c-augmented | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/c-diminished | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/c-flat-major | detail | original15 | TRUE | U083 | cb piano chord | 260 | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/c-m7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/c-m7-flat5 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/c-madd9 | detail | N2D_v2 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/c-maj7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/c-major | detail | original15 | TRUE | U081 | c chords piano | 480 | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/c-minor | detail | original15 | TRUE | U082 | c minor in piano | 260 | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/c-sharp-minor | detail | N1 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/c-sus2 | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/c-sus4 | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/d-7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/d-add9 | detail | N2D_v2 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/d-augmented | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/d-diminished | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/d-flat-7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/d-flat-add9 | detail | N2D_v2 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/d-flat-augmented | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/d-flat-diminished | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/d-flat-m7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/d-flat-m7-flat5 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/d-flat-madd9 | detail | N2D_v2 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/d-flat-maj7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/d-flat-major | detail | N1 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/d-flat-sus2 | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/d-flat-sus4 | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/d-m7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/d-m7-flat5 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/d-madd9 | detail | N2D_v2 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/d-maj7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/d-major | detail | N1 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/d-minor | detail | N1 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/d-sus2 | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/d-sus4 | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/diminished | category | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/e-7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/e-add9 | detail | N2D_v2 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/e-augmented | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/e-diminished | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/e-flat-7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/e-flat-add9 | detail | N2D_v2 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/e-flat-augmented | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/e-flat-diminished | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/e-flat-m7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/e-flat-m7-flat5 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/e-flat-madd9 | detail | N2D_v2 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/e-flat-maj7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/e-flat-major | detail | N1 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/e-flat-minor | detail | N1 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/e-flat-sus2 | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/e-flat-sus4 | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/e-m7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/e-m7-flat5 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/e-madd9 | detail | N2D_v2 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/e-maj7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/e-major | detail | original15 | TRUE | U080 | piano e chord | 590 | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/e-minor | detail | N1 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/e-sus2 | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/e-sus4 | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/f-7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/f-add9 | detail | N2D_v2 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/f-augmented | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/f-diminished | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/f-m7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/f-m7-flat5 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/f-madd9 | detail | N2D_v2 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/f-maj7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/f-major | detail | N1 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/f-minor | detail | N1 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/f-sharp-7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/f-sharp-add9 | detail | N2D_v2 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/f-sharp-augmented | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/f-sharp-diminished | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/f-sharp-m7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/f-sharp-m7-flat5 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/f-sharp-madd9 | detail | N2D_v2 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/f-sharp-maj7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/f-sharp-major | detail | N1 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/f-sharp-minor | detail | N1 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/f-sharp-sus2 | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/f-sharp-sus4 | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/f-sus2 | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/f-sus4 | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/finder | support | original15 | TRUE | U086 | chord finder piano | 1300 | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/g-7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/g-add9 | detail | N2D_v2 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/g-augmented | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/g-diminished | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/g-m7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/g-m7-flat5 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/g-madd9 | detail | N2D_v2 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/g-maj7 | detail | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/g-major | detail | original15 | TRUE | U084 | g chord piano |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/g-minor | detail | N1 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/g-sharp-minor | detail | N1 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/g-sus2 | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/g-sus4 | detail | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/major | category | N1 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/minor | category | N1 | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/seventh | category | N2C | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/chords/suspended | category | N2B | FALSE |  |  |  | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/guide/piano-chords | support | original15 | TRUE | U117 | how to play chords on piano | 1900 | reported_implemented | not_independently_verified | preserve_URL_and_correct_content
/keyboard-notes/finger-numbers | support | original15 | TRUE | U071 | piano fingering chart | 1300 | reported_implemented | not_independently_verified | preserve_URL_and_correct_content

## 原38任务
原38任务
证据口径：原规划来自附件；实现来自用户报告，待Codex以同一版本核对；预测数量不作强制指标。
任务ID | 原代表词 | 原目标 | 最终目标 | 当前证据 | 本轮动作 | 原交付要求 | 验证证据路径
P148 | piano chord chart | /chords | /chords | reported_limited | unified_lookup_all_supported_families | 默认有图表；根音/类型选择、试听、打印及读图说明。 | checks/chords-completion/task-evidence.json
P154 | minor chords piano | /chords#minor | /chords/minor | split_with_reported_category | preserve_minor_anchor_and_category | minor 选择后显示经过核对的实际和弦结果。 | checks/chords-completion/task-evidence.json
P158 | major chords piano | /chords#major | /chords/major | split_with_reported_category | preserve_major_anchor_and_category | major 选择后显示经过核对的实际和弦结果。 | checks/chords-completion/task-evidence.json
P168 | power chords piano | /chords#power | /chords#power | needs_completion | power_result_and_explanation | power chord 的实际结果与使用说明，不能只有标签。 | checks/chords-completion/task-evidence.json
P170 | piano chord chart 7th | /chords#seventh | /chords/seventh | split_and_partial | hub_seventh_examples_plus_category | 明确 7th 涉及的类别和输出；不把它无条件改成 major7。 | checks/chords-completion/task-evidence.json
P171 | piano chord chart jazz | /chords#jazz | /chords#jazz | needs_completion | jazz_examples_and_progression | jazz 相关和弦的实际示例及说明，不只加一个风格按钮。 | checks/chords-completion/task-evidence.json
P238 | major and minor chords piano | /chords#major-vs-minor | /chords#major-vs-minor | reported_implementation_exists_content_task_needs_evidence | retain_and_verify_against_required_output | 大小和弦对比包含音图/示例和区别，不用类型筛选器代替解释。 | checks/chords-completion/task-evidence.json
P247 | how to read a piano chord chart? | /chords#how-to-read | /chords#how-to-read | reported_implementation_exists_content_task_needs_evidence | retain_and_verify_against_required_output | 如何读键盘图、组成音和标记；深入学习连接指南。 | checks/chords-completion/task-evidence.json
P149 | a chord piano | /chords/a-major | /chords/a-major | reported_implementation_exists_content_task_needs_evidence | retain_and_verify_against_required_output | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接 | checks/chords-completion/task-evidence.json
P151 | am piano chord | /chords/a-minor | /chords/a-minor | reported_implementation_exists_content_task_needs_evidence | retain_and_verify_against_required_output | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接 | checks/chords-completion/task-evidence.json
P163 | c chords piano | /chords/c-major | /chords/c-major | reported_implementation_exists_content_task_needs_evidence | retain_and_verify_against_required_output | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接 | checks/chords-completion/task-evidence.json
P126 | piano fingering chart | /keyboard-notes/finger-numbers | /keyboard-notes/finger-numbers | reported_delivered_limited | preserve_hand_numbers_not_universal_fingering | 左右手编号图；基础使用说明；链接到具体和弦/音阶指法 | checks/chords-completion/task-evidence.json
P150 | b chord piano | /chords/b-major | /chords/b-major | reported_implementation_exists_content_task_needs_evidence | retain_and_verify_against_required_output | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接 | checks/chords-completion/task-evidence.json
P155 | a flat chord piano | /chords/a-flat-major | /chords/a-flat-major | reported_implementation_exists_content_task_needs_evidence | retain_and_verify_against_required_output | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接 | checks/chords-completion/task-evidence.json
P162 | piano e chord | /chords/e-major | /chords/e-major | reported_implementation_exists_content_task_needs_evidence | retain_and_verify_against_required_output | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接 | checks/chords-completion/task-evidence.json
P166 | c minor in piano | /chords/c-minor | /chords/c-minor | reported_implementation_exists_content_task_needs_evidence | retain_and_verify_against_required_output | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接 | checks/chords-completion/task-evidence.json
P167 | cb piano chord | /chords/c-flat-major | /chords/c-flat-major | reported_implementation_exists_content_task_needs_evidence | retain_and_verify_against_required_output | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接 | checks/chords-completion/task-evidence.json
P169 | g chord piano | /chords/g-major | /chords/g-major | reported_implementation_exists_content_task_needs_evidence | retain_and_verify_against_required_output | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接 | checks/chords-completion/task-evidence.json
P152 | chords of key | /chords/by-key | /chords/by-key | reported_implementation_exists_content_task_needs_evidence | retain_and_verify_against_required_output | 有内容的调性选择器与各级和弦表；支持已有G/D/C/E/A/F及D minor任务 | checks/chords-completion/task-evidence.json
P156 | chords in g major scale piano | /chords/by-key#g-major | /chords/by-key#g-major | reported_implementation_exists_content_task_needs_evidence | retain_and_verify_against_required_output | 查G大调各级和弦；必须在该页提供实际结果，不只增加一个关键词。 | checks/chords-completion/task-evidence.json
P157 | d major scale piano chords | /chords/by-key#d-major | /chords/by-key#d-major | reported_implementation_exists_content_task_needs_evidence | retain_and_verify_against_required_output | 查D大调各级和弦；必须在该页提供实际结果，不只增加一个关键词。 | checks/chords-completion/task-evidence.json
P159 | c major scale chords piano | /chords/by-key#c-major | /chords/by-key#c-major | reported_implementation_exists_content_task_needs_evidence | retain_and_verify_against_required_output | 查C大调各级和弦；必须在该页提供实际结果，不只增加一个关键词。 | checks/chords-completion/task-evidence.json
P160 | piano chords in e | /chords/by-key#e-major | /chords/by-key#e-major | reported_implementation_exists_content_task_needs_evidence | retain_and_verify_against_required_output | 查E大调各级和弦；必须在该页提供实际结果，不只增加一个关键词。 | checks/chords-completion/task-evidence.json
P161 | piano chords in a | /chords/by-key#a-major | /chords/by-key#a-major | reported_implementation_exists_content_task_needs_evidence | retain_and_verify_against_required_output | 查询A大调和弦集合；必须在该页提供实际结果，不只增加一个关键词。 | checks/chords-completion/task-evidence.json
P164 | key of f chords piano | /chords/by-key#f-major | /chords/by-key#f-major | reported_implementation_exists_content_task_needs_evidence | retain_and_verify_against_required_output | 查F大调各级和弦；必须在该页提供实际结果，不只增加一个关键词。 | checks/chords-completion/task-evidence.json
P165 | d minor scale piano chords | /chords/by-key#d-minor | /chords/by-key#d-minor | reported_implementation_exists_content_task_needs_evidence | retain_and_verify_against_required_output | 查D小调各级和弦；必须在该页提供实际结果，不只增加一个关键词。 | checks/chords-completion/task-evidence.json
P153 | chord finder piano | /chords/finder | /chords/finder | reported_limited | cross_family_finder | 选择音符；列出可能命名、低音与拼写说明 | checks/chords-completion/task-evidence.json
P172 | common chord progressions | /chord-progressions#common | /chord-progressions#common | reported_implementation_exists_content_task_needs_evidence | retain_and_verify_against_required_output | 常见和弦走向集合；必须在该页提供实际结果，不只增加一个关键词。 | checks/chords-completion/task-evidence.json
P173 | piano chord progressions | /chord-progressions | /chord-progressions | reported_implementation_exists_content_task_needs_evidence | retain_and_verify_against_required_output | 常见走向列表；C/E/A调转写选择；优美/愉快效果标签；含义与使用说明；打印 | checks/chords-completion/task-evidence.json
P174 | c major chord progressions | /chord-progressions#c-major | /chord-progressions#c-major | reported_implementation_exists_content_task_needs_evidence | retain_and_verify_against_required_output | C大调和弦走向；必须在该页提供实际结果，不只增加一个关键词。 | checks/chords-completion/task-evidence.json
P175 | common chord progressions key of e | /chord-progressions#e-major | /chord-progressions#e-major | reported_implementation_exists_content_task_needs_evidence | retain_and_verify_against_required_output | E调常用和弦走向；必须在该页提供实际结果，不只增加一个关键词。 | checks/chords-completion/task-evidence.json
P176 | a major chord progression | /chord-progressions#a-major | /chord-progressions#a-major | reported_implementation_exists_content_task_needs_evidence | retain_and_verify_against_required_output | A大调和弦走向；必须在该页提供实际结果，不只增加一个关键词。 | checks/chords-completion/task-evidence.json
P177 | beautiful chord progressions piano | /chord-progressions#beautiful | /chord-progressions#beautiful | not_proven_by_page_tests | subjective_example_with_controls | 查询优美钢琴和弦走向；必须在该页提供实际结果，不只增加一个关键词。 | checks/chords-completion/task-evidence.json
P178 | happy chord progressions | /chord-progressions#happy | /chord-progressions#happy | not_proven_by_page_tests | subjective_example_with_controls | 愉快情绪和弦走向；必须在该页提供实际结果，不只增加一个关键词。 | checks/chords-completion/task-evidence.json
P237 | what are chord progressions | /chord-progressions#how-it-works | /chord-progressions#how-it-works | reported_implementation_exists_content_task_needs_evidence | retain_and_verify_against_required_output | 说明走向是什么，附可试弹例子。 | checks/chords-completion/task-evidence.json
P220 | how to play chords on piano | /guide/piano-chords | /guide/piano-chords | reported_implementation_exists_content_task_needs_evidence | retain_and_verify_against_required_output | 步骤、构成、指法示意及连接练习；链接查图工具 | checks/chords-completion/task-evidence.json
P225 | basic piano chords | /guide/piano-chords#beginner | /guide/piano-chords#beginner | reported_implementation_exists_content_task_needs_evidence | retain_and_verify_against_required_output | 初学钢琴基础和弦选择与弹法；必须在该页提供实际结果，不只增加一个关键词。 | checks/chords-completion/task-evidence.json
P242 | piano chord transitions | /guide/piano-chords#transitions | /guide/piano-chords#transitions | not_proven_by_page_tests | guided_transitions | 练习钢琴和弦连接/换和弦动作；必须在该页提供实际结果，不只增加一个关键词。 | checks/chords-completion/task-evidence.json

## 原127范围
原127范围
证据口径：原规划来自附件；实现来自用户报告，待Codex以同一版本核对；预测数量不作强制指标。
原ID | URL | 原分类 | 模块归属 | 原代表词 | 原US量 | 原优先级 | 实现证据 | 本轮动作
U001 | / | site | other_module |  |  | 先做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U002 | /tools | site | other_module |  |  | 先做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U003 | /songs | songs | other_module | piano songs | 14800 | 先做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U004 | /songs/easy | songs | other_module | easy piano songs | 18100 | 先做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U036 | /tools/blank-sheet-music | sheet_music | other_module | empty piano sheet music | 390 | 先做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U067 | /keyboard-notes | keyboard_notes | other_module | piano keys | 33100 | 先做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U068 | /keyboard-notes/labeled | keyboard_notes | other_module | keys on a piano keyboard labeled | 12100 | 先做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U069 | /keyboard-notes/chart | keyboard_notes | other_module | piano notes chart | 4400 | 先做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U075 | /chords | chords | core_chords | piano chord chart | 6600 | 先做 | user_report_exists | preserve_and_finish_tasks
U076 | /chords/a-major | chords | core_chords | a chord piano | 4400 | 先做 | user_report_exists | preserve_and_finish_tasks
U078 | /chords/a-minor | chords | core_chords | am piano chord | 1900 | 先做 | user_report_exists | preserve_and_finish_tasks
U081 | /chords/c-major | chords | core_chords | c chords piano | 480 | 先做 | user_report_exists | preserve_and_finish_tasks
U088 | /scales | scales | other_module | piano scales | 6600 | 先做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U090 | /scales/c-major | scales | other_module | c major scale piano | 1300 | 先做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U091 | /scales/a-minor | scales | other_module | a minor scale piano | 1000 | 先做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U114 | /guide | guide | other_module | how to play piano for beginners | 1300 | 先做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U115 | /guide/read-sheet-music | guide | other_module | how to read sheet music piano | 18100 | 先做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U005 | /songs/christmas | songs | other_module | easy christmas songs in piano | 2900 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U006 | /songs/challenging | songs | other_module | hardest piano song | 1900 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U007 | /songs/pop | songs | other_module | easiest pop piano songs | 1300 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U008 | /songs/classical | songs | other_module | classical piano songs | 1000 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U009 | /songs/easy-chords | songs | adjacent_dependency | easy chords songs for beginners piano | 880 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U010 | /songs/anime | songs | other_module | most lovely piano anime songs | 880 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U011 | /songs/minecraft | songs | other_module | piano minecraft songs | 880 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U012 | /songs/rock | songs | other_module | piano rock songs | 720 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U013 | /songs/taylor-swift | songs | other_module | taylor swift piano songs | 720 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U014 | /songs/disney | songs | other_module | disney easy piano songs | 590 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U015 | /songs/wedding | songs | other_module | piano wedding songs | 590 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U016 | /songs/worship | songs | other_module | piano worship songs | 480 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U017 | /songs/rap | songs | other_module | rap songs for piano | 480 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U018 | /songs/piano-and-guitar | songs | other_module | piano and guitar songs | 390 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U019 | /songs/beatles | songs | other_module | beatles piano songs | 320 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U020 | /songs/coldplay | songs | other_module | coldplay piano songs | 320 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U021 | /songs/country | songs | other_module | country music piano songs | 320 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U022 | /songs/jazz | songs | other_module | jazz piano songs | 320 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U023 | /songs/halloween | songs | other_module | piano songs for halloween | 320 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U024 | /songs/undertale | songs | other_module | undertale songs on piano | 320 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U025 | /sheet-music | sheet_music | other_module | piano music sheet | 2900 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U026 | /sheet-music/easy | sheet_music | other_module | easy piano sheet music | 8100 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U027 | /sheet-music/beginner | sheet_music | other_module | beginner piano sheet music | 6600 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U028 | /sheet-music/christmas | sheet_music | other_module | christmas songs piano score | 2900 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U029 | /sheet-music/letter-notes | sheet_music | other_module | songs with letters piano | 1900 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U030 | /sheet-music/annotated | sheet_music | other_module | piano sheet music with letters | 1600 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U031 | /sheet-music/lead-sheets | sheet_music | adjacent_dependency | piano chords songs | 1300 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U032 | /sheet-music/pop | sheet_music | other_module | popular piano sheet music | 480 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U033 | /sheet-music/disney | sheet_music | other_module | disney song piano sheet for beginners | 390 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U034 | /sheet-music/classical | sheet_music | other_module | classical piano sheet music |  | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U035 | /sheet-music/jazz | sheet_music | other_module | easy jazz piano sheet music |  | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U037 | /sheet-music/jingle-bells | sheet_music | other_module | jingle bells song sheet for piano | 2400 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U041 | /sheet-music/amazing-grace | sheet_music | other_module | amazing grace song sheet for piano | 1300 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U045 | /sheet-music/fur-elise | sheet_music | other_module | fur elise piano sheet music easy | 720 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U048 | /sheet-music/happy-birthday | sheet_music | other_module | happy birthday sheet music piano easy | 480 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U052 | /sheet-music/hot-cross-buns | sheet_music | other_module | hot cross buns piano keys | 320 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U054 | /sheet-music/jesus-loves-me | sheet_music | other_module | jesus loves me piano keys | 320 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U061 | /sheet-music/mary-had-a-little-lamb | sheet_music | other_module | mary had a little lamb piano keys | 260 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U062 | /sheet-music/abc-song | sheet_music | other_module | abc song piano sheet |  | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U064 | /sheet-music/ode-to-joy | sheet_music | other_module | ode to joy easy piano sheet music |  | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U065 | /sheet-music/silent-night | sheet_music | other_module | silent night beginner piano sheet music |  | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U066 | /sheet-music/twinkle-twinkle-little-star | sheet_music | other_module | twinkle twinkle little star piano sheet music |  | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U070 | /keyboard-notes/frequencies | keyboard_notes | other_module | note frequency chart | 1300 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U071 | /keyboard-notes/finger-numbers | keyboard_notes | core_chords | piano fingering chart | 1300 | 后做 | user_report_exists | preserve_and_finish_tasks
U072 | /keyboard-notes/blank | keyboard_notes | other_module | piano keys blank page | 880 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U073 | /tools/piano-cheat-sheet | keyboard_notes | adjacent_dependency | piano cheat sheet | 590 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U074 | /keyboard-notes/key-signatures | keyboard_notes | adjacent_dependency | piano key signatures | 480 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U077 | /chords/b-major | chords | core_chords | b chord piano | 3600 | 后做 | user_report_exists | preserve_and_finish_tasks
U079 | /chords/a-flat-major | chords | core_chords | a flat chord piano | 1000 | 后做 | user_report_exists | preserve_and_finish_tasks
U080 | /chords/e-major | chords | core_chords | piano e chord | 590 | 后做 | user_report_exists | preserve_and_finish_tasks
U082 | /chords/c-minor | chords | core_chords | c minor in piano | 260 | 后做 | user_report_exists | preserve_and_finish_tasks
U083 | /chords/c-flat-major | chords | core_chords | cb piano chord | 260 | 后做 | user_report_exists | preserve_and_finish_tasks
U084 | /chords/g-major | chords | core_chords | g chord piano |  | 后做 | user_report_exists | preserve_and_finish_tasks
U085 | /chords/by-key | chords | core_chords | chords of key | 1900 | 后做 | user_report_exists | preserve_and_finish_tasks
U086 | /chords/finder | chords | core_chords | chord finder piano | 1300 | 后做 | user_report_exists | preserve_and_finish_tasks
U087 | /chord-progressions | chord_progressions | core_chords | piano chord progressions | 1600 | 后做 | user_report_exists | preserve_and_finish_tasks
U089 | /scales/modes | scales | other_module | scale modes | 1600 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U092 | /scales/blues | scales | other_module | blues scale piano | 1000 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U093 | /scales/d-major | scales | other_module | d major scale piano | 1000 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U094 | /scales/e-minor | scales | other_module | e minor scale piano | 1000 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U095 | /scales/f-major | scales | other_module | f major scale for piano | 1000 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U096 | /scales/g-major | scales | other_module | g major scale piano | 1000 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U097 | /scales/pentatonic | scales | other_module | pentatonic scale piano | 1000 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U098 | /scales/a-major | scales | other_module | a major scale for piano | 880 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U099 | /scales/c-minor | scales | other_module | c minor scale piano | 880 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U100 | /scales/d-minor | scales | other_module | d minor scale piano | 880 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U101 | /scales/e-major | scales | other_module | e major scale piano | 880 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U102 | /scales/b-minor | scales | other_module | b minor scale piano | 720 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U103 | /scales/f-minor | scales | other_module | f minor scale piano | 720 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U104 | /scales/harmonic-major | scales | other_module | harmonic major scale | 720 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U105 | /scales/a-sharp-minor | scales | other_module | a# minor scale | 590 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U106 | /scales/b-major | scales | other_module | b major scale piano | 590 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U107 | /scales/b-flat-major | scales | other_module | b flat major scale piano | 480 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U108 | /scales/g-minor | scales | other_module | g minor scale piano | 480 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U109 | /scales/chromatic | scales | other_module | chromatic scale piano | 390 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U110 | /scales/e-flat-major | scales | other_module | e flat major scale piano | 390 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U111 | /scales/f-sharp-minor | scales | other_module | f#m piano scale | 390 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U112 | /scales/c-flat-major | scales | other_module | cb major scale piano | 320 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U113 | /arpeggios | arpeggios | adjacent_dependency | arpeggios piano |  | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U116 | /guide/sight-reading | guide | other_module | sight reading piano tips for improvement | 12100 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U117 | /guide/piano-chords | guide | core_chords | how to play chords on piano | 1900 | 后做 | user_report_exists | preserve_and_finish_tasks
U118 | /guide/piano-books | guide | other_module | piano books for beginners | 1900 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U119 | /guide/learn-a-piano-song | guide | adjacent_dependency | how to play piano songs | 880 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U120 | /guide/piano-scales | guide | other_module | piano scales for beginners | 880 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U121 | /guide/compose-a-piano-song | guide | other_module | make a piano song | 320 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U122 | /guide/hanon-exercises | guide | other_module | hanon piano exercises |  | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U123 | /guide/note-values-and-rhythm | guide | adjacent_dependency | kinds of notes music | 1300 | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U124 | /guide/piano-exercises | guide | adjacent_dependency | piano exercises for beginners |  | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U125 | /guide/piano-hand-position | guide | adjacent_dependency | piano hand posture |  | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U126 | /guide/piano-practice | guide | adjacent_dependency | piano practice |  | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U127 | /guide/music-symbols-and-piano-terms | guide | adjacent_dependency | piano terms |  | 后做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U038 | /sheet-music/let-it-go | sheet_music | other_module | frozen let it go piano sheet music easy free pdf | 1600 | 暂不做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U039 | /sheet-music/super-mario-theme | sheet_music | other_module | super mario theme piano sheet music easy free pdf | 1600 | 暂不做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U040 | /sheet-music/thats-amore | sheet_music | other_module | what are the piano keys to thats amore | 1600 | 暂不做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U042 | /sheet-music/black-parade | sheet_music | other_module | black parade keys piano | 1300 | 暂不做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U043 | /sheet-music/clocks | sheet_music | other_module | clocks piano keys | 1300 | 暂不做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U044 | /sheet-music/from-the-start | sheet_music | other_module | from the start piano sheet music | 880 | 暂不做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U046 | /sheet-music/song-of-storms | sheet_music | other_module | song of storms piano sheet music | 720 | 暂不做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U047 | /sheet-music/pink-panther | sheet_music | other_module | pink panther theme song piano sheet | 590 | 暂不做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U049 | /sheet-music/still-dre | sheet_music | other_module | piano keys for still dre | 480 | 暂不做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U050 | /sheet-music/carol-of-the-bells | sheet_music | other_module | carol of the bells easy piano sheet music | 390 | 暂不做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U051 | /sheet-music/edelweiss | sheet_music | other_module | edelweiss song piano sheet | 320 | 暂不做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U053 | /sheet-music/in-my-life | sheet_music | other_module | in my life piano sheet music | 320 | 暂不做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U055 | /sheet-music/all-of-me-john-legend | sheet_music | other_module | john legend all of me piano keys | 320 | 暂不做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U056 | /sheet-music/runaway-kanye-west | sheet_music | other_module | piano keys for runaway kanye west | 320 | 暂不做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U057 | /sheet-music/piano-man | sheet_music | other_module | piano man sheet music easy | 320 | 暂不做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U058 | /sheet-music/someone-like-you-adele | sheet_music | other_module | someone like you adele piano keys | 320 | 暂不做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U059 | /sheet-music/song-of-healing | sheet_music | other_module | song of healing piano sheet music | 320 | 暂不做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U060 | /sheet-music/a-whole-new-world | sheet_music | other_module | a whole new world piano keys | 260 | 暂不做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release
U063 | /sheet-music/easy-on-me | sheet_music | other_module | easy on me piano sheet music |  | 暂不做 | not_established_by_this_chords_audit | preserve_original_plan_no_auto_release

## 原191关键词
原191关键词
证据口径：原规划来自附件；实现来自用户报告，待Codex以同一版本核对；预测数量不作强制指标。
关键词ID | 原关键词 | 原US量 | 原归并关系 | 原任务ID | 原URL | 同页分区 | 原来源位置 | 原交付要求
K0018 | piano chord chart | 6600 | 页面代表词 | P148 | /chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A296:G296; 关键词策略构建器数据汇总.md｜L73｜piano chord chart > piano chord chart; 关键词策略构建器数据汇总.md｜L318｜beginner piano sheet music > easy piano sheet music with chords; 关键词策略构建器数据汇总.md｜L460｜piano scales > piano chords and progressions | 默认有图表；根音/类型选择、试听、打印及读图说明。
K0027 | keyboard chord sheet | 5400 | 同义词合并 | P148 | /chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A298:G298 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K0030 | a chord piano | 4400 | 页面代表词 | P149 | /chords/a-major |  | piano_keyword_research_combined.xlsx｜关键词数据!A299:G299; 关键词策略构建器数据汇总.md｜L74｜piano chord chart > piano chord chart; 关键词策略构建器数据汇总.md｜L319｜beginner piano sheet music > easy piano sheet music with chords; 关键词策略构建器数据汇总.md｜L461｜piano scales > piano chords and progressions | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K0037 | b chord piano | 3600 | 页面代表词 | P150 | /chords/b-major |  | piano_keyword_research_combined.xlsx｜关键词数据!A300:G300; 关键词策略构建器数据汇总.md｜L512｜piano scales > piano scales and fingering | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K0052 | keyboard chord chart | 2900 | 同义词合并 | P148 | /chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A302:G302 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K0059 | a piano chord | 2400 | 同义词合并 | P149 | /chords/a-major |  | piano_keyword_research_combined.xlsx｜关键词数据!A304:G304 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K0060 | b piano chord | 2400 | 同义词合并 | P150 | /chords/b-major |  | piano_keyword_research_combined.xlsx｜关键词数据!A305:G305 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K0062 | common chord progressions | 2400 | 页面代表词 | P172 | /chord-progressions | common | piano_keyword_research_combined.xlsx｜关键词数据!A307:G307 | 常见和弦走向集合；必须在该页提供实际结果，不只增加一个关键词。
K0073 | am piano chord | 1900 | 页面代表词 | P151 | /chords/a-minor |  | piano_keyword_research_combined.xlsx｜关键词数据!A308:G308 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K0074 | chords of key | 1900 | 页面代表词 | P152 | /chords/by-key |  | piano_keyword_research_combined.xlsx｜关键词数据!A310:G310; 关键词策略构建器数据汇总.md｜L322｜beginner piano sheet music > easy piano sheet music with chords | 有内容的调性选择器与各级和弦表；支持已有G/D/C/E/A/F及D minor任务
K0082 | how to play chords on piano | 1900 | 页面代表词 | P220 | /guide/piano-chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A311:G311 | 步骤、构成、指法示意及连接练习；链接查图工具
K0086 | music chord charts piano | 1900 | 同义词合并 | P148 | /chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A313:G313 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K0100 | chord chart piano | 1600 | 同义词合并 | P148 | /chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A314:G314 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K0116 | piano chord progressions | 1600 | 页面代表词 | P173 | /chord-progressions |  | piano_keyword_research_combined.xlsx｜关键词数据!A295:G295; 关键词策略构建器数据汇总.md｜L107｜piano chord chart > piano chord accompaniment; 关键词策略构建器数据汇总.md｜L464｜piano scales > piano chords and progressions; piano_keyword_research_combined.xlsx｜关键词数据!A317:G317; 关键词策略构建器数据汇总.md｜L325｜beginner piano sheet music > easy piano sheet music with chords | 常见走向列表；C/E/A调转写选择；优美/愉快效果标签；含义与使用说明；打印
K0132 | a major chord piano | 1300 | 同义词合并 | P149 | /chords/a-major |  | piano_keyword_research_combined.xlsx｜关键词数据!A320:G320 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K0134 | am on piano chord | 1300 | 同义词合并 | P151 | /chords/a-minor |  | piano_keyword_research_combined.xlsx｜关键词数据!A322:G322 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K0136 | b major chord in piano | 1300 | 同义词合并 | P150 | /chords/b-major |  | piano_keyword_research_combined.xlsx｜关键词数据!A323:G323 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K0137 | b major chords on piano | 1300 | 同义词合并 | P150 | /chords/b-major |  | piano_keyword_research_combined.xlsx｜关键词数据!A324:G324 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K0138 | basic piano chords | 1300 | 页面代表词 | P225 | /guide/piano-chords | beginner | piano_keyword_research_combined.xlsx｜关键词数据!A325:G325 | 初学钢琴基础和弦选择与弹法；必须在该页提供实际结果，不只增加一个关键词。
K0145 | chord b on piano | 1300 | 同义词合并 | P150 | /chords/b-major |  | piano_keyword_research_combined.xlsx｜关键词数据!A326:G326 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K0146 | chord finder piano | 1300 | 页面代表词 | P153 | /chords/finder |  | piano_keyword_research_combined.xlsx｜关键词数据!A327:G327 | 选择音符；列出可能命名、低音与拼写说明
K0147 | chords in the key of a | 1300 | 同页补充/条件/问题（非同义） | P161 | /chords/by-key | a-major | piano_keyword_research_combined.xlsx｜关键词数据!A328:G328 | 查询A大调和弦集合；必须在该页提供实际结果，不只增加一个关键词。
K0170 | minor chords piano | 1300 | 页面代表词 | P154 | /chords | minor | piano_keyword_research_combined.xlsx｜关键词数据!A330:G330 | minor 选择后显示经过核对的实际和弦结果。
K0177 | piano fingering chart | 1300 | 页面代表词 | P126 | /keyboard-notes/finger-numbers |  | piano_keyword_research_combined.xlsx｜关键词数据!A45:G45; 关键词策略构建器数据汇总.md｜L510｜piano scales > piano scales and fingering | 左右手编号图；基础使用说明；链接到具体和弦/音阶指法
K0187 | a flat chord piano | 1000 | 页面代表词 | P155 | /chords/a-flat-major |  | piano_keyword_research_combined.xlsx｜关键词数据!A335:G335 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K0188 | a flat piano chord | 1000 | 同义词合并 | P155 | /chords/a-flat-major |  | piano_keyword_research_combined.xlsx｜关键词数据!A336:G336 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K0189 | a minor piano chord | 1000 | 同义词合并 | P151 | /chords/a-minor |  | piano_keyword_research_combined.xlsx｜关键词数据!A337:G337 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K0196 | chords in g major scale piano | 1000 | 页面代表词 | P156 | /chords/by-key | g-major | piano_keyword_research_combined.xlsx｜关键词数据!A49:G49 | 查G大调各级和弦；必须在该页提供实际结果，不只增加一个关键词。
K0197 | chords of a major key | 1000 | 同页补充/条件/问题（非同义） | P161 | /chords/by-key | a-major | piano_keyword_research_combined.xlsx｜关键词数据!A338:G338 | 查询A大调和弦集合；必须在该页提供实际结果，不只增加一个关键词。
K0224 | major key chords | 1000 | 同义词合并 | P152 | /chords/by-key |  | piano_keyword_research_combined.xlsx｜关键词数据!A339:G339 | 有内容的调性选择器与各级和弦表；支持已有G/D/C/E/A/F及D minor任务
K0238 | piano chords and progressions | 1000 | 同义词合并 | P173 | /chord-progressions |  | piano_keyword_research_combined.xlsx｜关键词数据!A342:G342 | 常见走向列表；C/E/A调转写选择；优美/愉快效果标签；含义与使用说明；打印
K0260 | a major key chords | 880 | 同页补充/条件/问题（非同义） | P161 | /chords/by-key | a-major | piano_keyword_research_combined.xlsx｜关键词数据!A346:G346 | 查询A大调和弦集合；必须在该页提供实际结果，不只增加一个关键词。
K0266 | chord progressions piano | 880 | 同义词合并 | P173 | /chord-progressions |  | piano_keyword_research_combined.xlsx｜关键词数据!A348:G348 | 常见走向列表；C/E/A调转写选择；优美/愉快效果标签；含义与使用说明；打印
K0267 | chords in the key of a major | 880 | 同页补充/条件/问题（非同义） | P161 | /chords/by-key | a-major | piano_keyword_research_combined.xlsx｜关键词数据!A349:G349 | 查询A大调和弦集合；必须在该页提供实际结果，不只增加一个关键词。
K0268 | d major scale piano chords | 880 | 页面代表词 | P157 | /chords/by-key | d-major | piano_keyword_research_combined.xlsx｜关键词数据!A74:G74 | 查D大调各级和弦；必须在该页提供实际结果，不只增加一个关键词。
K0275 | easy piano chords | 880 | 同义词合并 | P225 | /guide/piano-chords | beginner | piano_keyword_research_combined.xlsx｜关键词数据!A351:G351 | 初学钢琴基础和弦选择与弹法；必须在该页提供实际结果，不只增加一个关键词。
K0288 | g major scale piano chords | 880 | 同义词合并 | P156 | /chords/by-key | g-major | piano_keyword_research_combined.xlsx｜关键词数据!A83:G83 | 查G大调各级和弦；必须在该页提供实际结果，不只增加一个关键词。
K0294 | major chords piano | 880 | 页面代表词 | P158 | /chords | major | piano_keyword_research_combined.xlsx｜关键词数据!A352:G352 | major 选择后显示经过核对的实际和弦结果。
K0318 | popular chord progressions | 880 | 同义词合并 | P172 | /chord-progressions | common | piano_keyword_research_combined.xlsx｜关键词数据!A355:G355 | 常见和弦走向集合；必须在该页提供实际结果，不只增加一个关键词。
K0334 | a major piano chord | 720 | 同义词合并 | P149 | /chords/a-major |  | piano_keyword_research_combined.xlsx｜关键词数据!A356:G356 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K0335 | a major scale chords | 720 | 同页补充/条件/问题（非同义） | P161 | /chords/by-key | a-major | piano_keyword_research_combined.xlsx｜关键词数据!A98:G98 | 查询A大调和弦集合；必须在该页提供实际结果，不只增加一个关键词。
K0343 | c major scale chords piano | 720 | 页面代表词 | P159 | /chords/by-key | c-major | piano_keyword_research_combined.xlsx｜关键词数据!A102:G102 | 查C大调各级和弦；必须在该页提供实际结果，不只增加一个关键词。
K0345 | chord sequences | 720 | 同页补充/条件/问题（非同义） | P173 | /chord-progressions |  | piano_keyword_research_combined.xlsx｜关键词数据!A359:G359 | 常见走向列表；C/E/A调转写选择；优美/愉快效果标签；含义与使用说明；打印
K0346 | chords for the key of a | 720 | 同页补充/条件/问题（非同义） | P161 | /chords/by-key | a-major | piano_keyword_research_combined.xlsx｜关键词数据!A361:G361 | 查询A大调和弦集合；必须在该页提供实际结果，不只增加一个关键词。
K0347 | chords key a | 720 | 同页补充/条件/问题（非同义） | P161 | /chords/by-key | a-major | piano_keyword_research_combined.xlsx｜关键词数据!A362:G362 | 查询A大调和弦集合；必须在该页提供实际结果，不只增加一个关键词。
K0380 | key of a chords | 720 | 同页补充/条件/问题（非同义） | P161 | /chords/by-key | a-major | piano_keyword_research_combined.xlsx｜关键词数据!A363:G363 | 查询A大调和弦集合；必须在该页提供实际结果，不只增加一个关键词。
K0388 | minor chords on the piano | 720 | 同义词合并 | P154 | /chords | minor | piano_keyword_research_combined.xlsx｜关键词数据!A364:G364 | minor 选择后显示经过核对的实际和弦结果。
K0390 | most common chord progressions | 720 | 同义词合并 | P172 | /chord-progressions | common | piano_keyword_research_combined.xlsx｜关键词数据!A365:G365 | 常见和弦走向集合；必须在该页提供实际结果，不只增加一个关键词。
K0402 | piano chord sequences | 720 | 同义词合并 | P173 | /chord-progressions |  | piano_keyword_research_combined.xlsx｜关键词数据!A368:G368 | 常见走向列表；C/E/A调转写选择；优美/愉快效果标签；含义与使用说明；打印
K0403 | piano chords in e | 720 | 页面代表词 | P160 | /chords/by-key | e-major | piano_keyword_research_combined.xlsx｜关键词数据!A369:G369 | 查E大调各级和弦；必须在该页提供实际结果，不只增加一个关键词。
K0404 | piano chords in key of g | 720 | 同义词合并 | P156 | /chords/by-key | g-major | piano_keyword_research_combined.xlsx｜关键词数据!A370:G370 | 查G大调各级和弦；必须在该页提供实际结果，不只增加一个关键词。
K0413 | piano progressions | 720 | 同义词合并 | P173 | /chord-progressions |  | piano_keyword_research_combined.xlsx｜关键词数据!A371:G371 | 常见走向列表；C/E/A调转写选择；优美/愉快效果标签；含义与使用说明；打印
K0430 | a chord on piano | 590 | 同义词合并 | P149 | /chords/a-major |  | piano_keyword_research_combined.xlsx｜关键词数据!A373:G373 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K0433 | all chords on a piano | 590 | 同义词合并 | P148 | /chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A374:G374 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K0434 | b chord on piano | 590 | 同义词合并 | P150 | /chords/b-major |  | piano_keyword_research_combined.xlsx｜关键词数据!A375:G375 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K0444 | c major chord progressions | 590 | 页面代表词 | P174 | /chord-progressions | c-major | piano_keyword_research_combined.xlsx｜关键词数据!A377:G377 | C大调和弦走向；必须在该页提供实际结果，不只增加一个关键词。
K0447 | chord patterns piano | 590 | 同义词合并 | P173 | /chord-progressions |  | piano_keyword_research_combined.xlsx｜关键词数据!A378:G378 | 常见走向列表；C/E/A调转写选择；优美/愉快效果标签；含义与使用说明；打印
K0448 | chords in a key | 590 | 同义词合并 | P152 | /chords/by-key |  | piano_keyword_research_combined.xlsx｜关键词数据!A379:G379 | 有内容的调性选择器与各级和弦表；支持已有G/D/C/E/A/F及D minor任务
K0450 | common chord progressions key of e | 590 | 页面代表词 | P175 | /chord-progressions | e-major | piano_keyword_research_combined.xlsx｜关键词数据!A380:G380 | E调常用和弦走向；必须在该页提供实际结果，不只增加一个关键词。
K0470 | famous chord progressions | 590 | 同义词合并 | P172 | /chord-progressions | common | piano_keyword_research_combined.xlsx｜关键词数据!A381:G381 | 常见和弦走向集合；必须在该页提供实际结果，不只增加一个关键词。
K0491 | key of g piano chords | 590 | 同义词合并 | P156 | /chords/by-key | g-major | piano_keyword_research_combined.xlsx｜关键词数据!A661:G661 | 查G大调各级和弦；必须在该页提供实际结果，不只增加一个关键词。
K0493 | keyboard chords | 590 | 同义词合并 | P148 | /chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A383:G383 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K0521 | piano chords in a | 590 | 页面代表词 | P161 | /chords/by-key | a-major | piano_keyword_research_combined.xlsx｜关键词数据!A388:G388 | 查询A大调和弦集合；必须在该页提供实际结果，不只增加一个关键词。
K0523 | piano e chord | 590 | 页面代表词 | P162 | /chords/e-major |  | piano_keyword_research_combined.xlsx｜关键词数据!A389:G389 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K0567 | ab chord on piano | 480 | 同义词合并 | P155 | /chords/a-flat-major |  | piano_keyword_research_combined.xlsx｜关键词数据!A393:G393 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K0575 | b chord on the piano | 480 | 同义词合并 | P150 | /chords/b-major |  | piano_keyword_research_combined.xlsx｜关键词数据!A396:G396 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K0578 | b major piano chord | 480 | 同义词合并 | P150 | /chords/b-major |  | piano_keyword_research_combined.xlsx｜关键词数据!A397:G397 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K0584 | c chords piano | 480 | 页面代表词 | P163 | /chords/c-major |  | piano_keyword_research_combined.xlsx｜关键词数据!A400:G400 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K0585 | c major scale piano chords | 480 | 同义词合并 | P159 | /chords/by-key | c-major | piano_keyword_research_combined.xlsx｜关键词数据!A165:G165 | 查C大调各级和弦；必须在该页提供实际结果，不只增加一个关键词。
K0586 | chord structure piano | 480 | 同页补充/条件/问题（非同义） | P220 | /guide/piano-chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A402:G402 | 步骤、构成、指法示意及连接练习；链接查图工具
K0587 | chords in key of a | 480 | 同页补充/条件/问题（非同义） | P161 | /chords/by-key | a-major | piano_keyword_research_combined.xlsx｜关键词数据!A403:G403 | 查询A大调和弦集合；必须在该页提供实际结果，不只增加一个关键词。
K0592 | cool chord progressions | 480 | 同页补充/条件/问题（非同义） | P177 | /chord-progressions | beautiful | piano_keyword_research_combined.xlsx｜关键词数据!A405:G405 | 查询优美钢琴和弦走向；必须在该页提供实际结果，不只增加一个关键词。
K0598 | e major scale chords piano | 480 | 同义词合并 | P160 | /chords/by-key | e-major | piano_keyword_research_combined.xlsx｜关键词数据!A170:G170 | 查E大调各级和弦；必须在该页提供实际结果，不只增加一个关键词。
K0627 | key of f chords piano | 480 | 页面代表词 | P164 | /chords/by-key | f-major | piano_keyword_research_combined.xlsx｜关键词数据!A712:G712 | 查F大调各级和弦；必须在该页提供实际结果，不只增加一个关键词。
K0628 | key of g chords piano | 480 | 同义词合并 | P156 | /chords/by-key | g-major | piano_keyword_research_combined.xlsx｜关键词数据!A713:G713 | 查G大调各级和弦；必须在该页提供实际结果，不只增加一个关键词。
K0657 | piano chord cheat sheet | 480 | 同义词合并 | P148 | /chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A409:G409; 关键词策略构建器数据汇总.md｜L79｜piano chord chart > piano chord chart; 关键词策略构建器数据汇总.md｜L465｜piano scales > piano chords and progressions | 默认有图表；根音/类型选择、试听、打印及读图说明。
K0658 | piano chord diagram | 480 | 同义词合并 | P148 | /chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A410:G410 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K0661 | piano finger chart | 480 | 同义词合并 | P126 | /keyboard-notes/finger-numbers |  | piano_keyword_research_combined.xlsx｜关键词数据!A187:G187 | 左右手编号图；基础使用说明；链接到具体和弦/音阶指法
K0664 | piano keyboard chords for beginners | 480 | 同义词合并 | P225 | /guide/piano-chords | beginner | piano_keyword_research_combined.xlsx｜关键词数据!A411:G411 | 初学钢琴基础和弦选择与弹法；必须在该页提供实际结果，不只增加一个关键词。
K0668 | piano major chords | 480 | 同义词合并 | P158 | /chords | major | piano_keyword_research_combined.xlsx｜关键词数据!A412:G412 | major 选择后显示经过核对的实际和弦结果。
K0671 | piano playing by chords | 480 | 同义词合并 | P220 | /guide/piano-chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A413:G413 | 步骤、构成、指法示意及连接练习；链接查图工具
K0705 | a flat chords piano | 390 | 同义词合并 | P155 | /chords/a-flat-major |  | piano_keyword_research_combined.xlsx｜关键词数据!A415:G415 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K0706 | a major chord progression | 390 | 页面代表词 | P176 | /chord-progressions | a-major | piano_keyword_research_combined.xlsx｜关键词数据!A416:G416 | A大调和弦走向；必须在该页提供实际结果，不只增加一个关键词。
K0708 | a minor chord on piano | 390 | 同义词合并 | P151 | /chords/a-minor |  | piano_keyword_research_combined.xlsx｜关键词数据!A417:G417 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K0709 | a minor chords piano | 390 | 同义词合并 | P151 | /chords/a-minor |  | piano_keyword_research_combined.xlsx｜关键词数据!A418:G418 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K0711 | all chords piano | 390 | 同义词合并 | P148 | /chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A419:G419 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K0714 | am chord on piano | 390 | 同义词合并 | P151 | /chords/a-minor |  | piano_keyword_research_combined.xlsx｜关键词数据!A421:G421 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K0716 | beautiful chord progressions | 390 | 同页补充/条件/问题（非同义） | P177 | /chord-progressions | beautiful | piano_keyword_research_combined.xlsx｜关键词数据!A422:G422 | 查询优美钢琴和弦走向；必须在该页提供实际结果，不只增加一个关键词。
K0728 | chord cheat sheet piano | 390 | 同义词合并 | P148 | /chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A424:G424 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K0729 | chord namer piano | 390 | 同义词合并 | P153 | /chords/finder |  | piano_keyword_research_combined.xlsx｜关键词数据!A425:G425 | 选择音符；列出可能命名、低音与拼写说明
K0730 | chord sheet piano | 390 | 同义词合并 | P148 | /chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A426:G426 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K0731 | chords in the a major scale | 390 | 同页补充/条件/问题（非同义） | P161 | /chords/by-key | a-major | piano_keyword_research_combined.xlsx｜关键词数据!A204:G204 | 查询A大调和弦集合；必须在该页提供实际结果，不只增加一个关键词。
K0732 | chords piano chart | 390 | 同义词合并 | P148 | /chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A427:G427 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K0756 | f major scale chords piano | 390 | 同义词合并 | P164 | /chords/by-key | f-major | piano_keyword_research_combined.xlsx｜关键词数据!A213:G213 | 查F大调各级和弦；必须在该页提供实际结果，不只增加一个关键词。
K0785 | key chord chart | 390 | 同义词合并 | P152 | /chords/by-key |  | piano_keyword_research_combined.xlsx｜关键词数据!A430:G430 | 有内容的调性选择器与各级和弦表；支持已有G/D/C/E/A/F及D minor任务
K0786 | key of f piano chords | 390 | 同义词合并 | P164 | /chords/by-key | f-major | piano_keyword_research_combined.xlsx｜关键词数据!A771:G771 | 查F大调各级和弦；必须在该页提供实际结果，不只增加一个关键词。
K0801 | major piano chords | 390 | 同义词合并 | P158 | /chords | major | piano_keyword_research_combined.xlsx｜关键词数据!A432:G432 | major 选择后显示经过核对的实际和弦结果。
K0806 | minor piano chords | 390 | 同义词合并 | P154 | /chords | minor | piano_keyword_research_combined.xlsx｜关键词数据!A433:G433 | minor 选择后显示经过核对的实际和弦结果。
K0823 | piano a flat chord | 390 | 同义词合并 | P155 | /chords/a-flat-major |  | piano_keyword_research_combined.xlsx｜关键词数据!A435:G435 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K0825 | piano basic chords | 390 | 同义词合并 | P225 | /guide/piano-chords | beginner | piano_keyword_research_combined.xlsx｜关键词数据!A436:G436 | 初学钢琴基础和弦选择与弹法；必须在该页提供实际结果，不只增加一个关键词。
K0826 | piano beginner chords | 390 | 同义词合并 | P225 | /guide/piano-chords | beginner | piano_keyword_research_combined.xlsx｜关键词数据!A437:G437 | 初学钢琴基础和弦选择与弹法；必须在该页提供实际结果，不只增加一个关键词。
K0830 | piano chord namer | 390 | 同义词合并 | P153 | /chords/finder |  | piano_keyword_research_combined.xlsx｜关键词数据!A438:G438 | 选择音符；列出可能命名、低音与拼写说明
K0831 | piano chords cheat sheet | 390 | 同义词合并 | P148 | /chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A439:G439 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K0849 | piano progression chords | 390 | 同义词合并 | P173 | /chord-progressions |  | piano_keyword_research_combined.xlsx｜关键词数据!A442:G442 | 常见走向列表；C/E/A调转写选择；优美/愉快效果标签；含义与使用说明；打印
K0879 | what are chord progressions | 390 | 页面代表词 | P237 | /chord-progressions | how-it-works | piano_keyword_research_combined.xlsx｜关键词数据!A444:G444 | 说明走向是什么，附可试弹例子。
K0888 | am in piano | 320 | 同义词合并 | P151 | /chords/a-minor |  | piano_keyword_research_combined.xlsx｜关键词数据!A447:G447 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K0891 | b chords piano | 320 | 同义词合并 | P150 | /chords/b-major |  | piano_keyword_research_combined.xlsx｜关键词数据!A448:G448 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K0895 | basic piano chord | 320 | 同义词合并 | P225 | /guide/piano-chords | beginner | piano_keyword_research_combined.xlsx｜关键词数据!A450:G450 | 初学钢琴基础和弦选择与弹法；必须在该页提供实际结果，不只增加一个关键词。
K0909 | chord progression piano | 320 | 同义词合并 | P173 | /chord-progressions |  | piano_keyword_research_combined.xlsx｜关键词数据!A452:G452 | 常见走向列表；C/E/A调转写选择；优美/愉快效果标签；含义与使用说明；打印
K0910 | chord sheets for piano | 320 | 同义词合并 | P148 | /chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A453:G453 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K0911 | chords for key of a | 320 | 同页补充/条件/问题（非同义） | P161 | /chords/by-key | a-major | piano_keyword_research_combined.xlsx｜关键词数据!A454:G454 | 查询A大调和弦集合；必须在该页提供实际结果，不只增加一个关键词。
K0913 | chords in key a | 320 | 同页补充/条件/问题（非同义） | P161 | /chords/by-key | a-major | piano_keyword_research_combined.xlsx｜关键词数据!A456:G456 | 查询A大调和弦集合；必须在该页提供实际结果，不只增加一个关键词。
K0914 | chords in the key of g piano | 320 | 同义词合并 | P156 | /chords/by-key | g-major | piano_keyword_research_combined.xlsx｜关键词数据!A825:G825 | 查G大调各级和弦；必须在该页提供实际结果，不只增加一个关键词。
K0920 | common chord patterns | 320 | 同义词合并 | P172 | /chord-progressions | common | piano_keyword_research_combined.xlsx｜关键词数据!A457:G457 | 常见和弦走向集合；必须在该页提供实际结果，不只增加一个关键词。
K0921 | common chord sequences | 320 | 同义词合并 | P172 | /chord-progressions | common | piano_keyword_research_combined.xlsx｜关键词数据!A458:G458 | 常见和弦走向集合；必须在该页提供实际结果，不只增加一个关键词。
K0922 | cool chord sequences | 320 | 同页补充/条件/问题（非同义） | P177 | /chord-progressions | beautiful | piano_keyword_research_combined.xlsx｜关键词数据!A459:G459 | 查询优美钢琴和弦走向；必须在该页提供实际结果，不只增加一个关键词。
K0925 | d major scale chords piano | 320 | 同义词合并 | P157 | /chords/by-key | d-major | piano_keyword_research_combined.xlsx｜关键词数据!A252:G252 | 查D大调各级和弦；必须在该页提供实际结果，不只增加一个关键词。
K0927 | d minor scale piano chords | 320 | 页面代表词 | P165 | /chords/by-key | d-minor | piano_keyword_research_combined.xlsx｜关键词数据!A254:G254 | 查D小调各级和弦；必须在该页提供实际结果，不只增加一个关键词。
K0939 | easy piano chord chart | 320 | 同页补充/条件/问题（非同义） | P148 | /chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A460:G460; Google 第2批 图10 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K0986 | key chords | 320 | 同义词合并 | P152 | /chords/by-key |  | piano_keyword_research_combined.xlsx｜关键词数据!A461:G461 | 有内容的调性选择器与各级和弦表；支持已有G/D/C/E/A/F及D minor任务
K0988 | keyboard chords chart | 320 | 同义词合并 | P148 | /chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A462:G462 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K1009 | major and minor chords piano | 320 | 页面代表词 | P238 | /chords | major-vs-minor | piano_keyword_research_combined.xlsx｜关键词数据!A266:G266 | 大小和弦对比包含音图/示例和区别，不用类型筛选器代替解释。
K1010 | major chords in piano | 320 | 同义词合并 | P158 | /chords | major | piano_keyword_research_combined.xlsx｜关键词数据!A267:G267 | major 选择后显示经过核对的实际和弦结果。
K1015 | minor piano chord | 320 | 同义词合并 | P154 | /chords | minor | piano_keyword_research_combined.xlsx｜关键词数据!A464:G464 | minor 选择后显示经过核对的实际和弦结果。
K1040 | piano a minor chord | 320 | 同义词合并 | P151 | /chords/a-minor |  | piano_keyword_research_combined.xlsx｜关键词数据!A465:G465 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K1043 | piano chord b | 320 | 同义词合并 | P150 | /chords/b-major |  | piano_keyword_research_combined.xlsx｜关键词数据!A466:G466 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K1044 | piano chord chart for beginners | 320 | 同页补充/条件/问题（非同义） | P148 | /chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A468:G468 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K1045 | piano chord charts | 320 | 同义词合并 | P148 | /chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A469:G469 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K1047 | piano chords in the key of f | 320 | 同义词合并 | P164 | /chords/by-key | f-major | piano_keyword_research_combined.xlsx｜关键词数据!A471:G471 | 查F大调各级和弦；必须在该页提供实际结果，不只增加一个关键词。
K1048 | piano chords sheet | 320 | 同义词合并 | P148 | /chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A472:G472 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K1049 | piano chords table | 320 | 同义词合并 | P148 | /chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A473:G473 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K1086 | printable piano chord chart | 320 | 同页补充/条件/问题（非同义） | P148 | /chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A477:G477 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K1117 | what chord is this piano | 320 | 同义词合并 | P153 | /chords/finder |  | piano_keyword_research_combined.xlsx｜关键词数据!A479:G479 | 选择音符；列出可能命名、低音与拼写说明
K1119 | a chords piano | 260 | 同义词合并 | P149 | /chords/a-major |  | piano_keyword_research_combined.xlsx｜关键词数据!A481:G481 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K1120 | a minor chord for piano | 260 | 同义词合并 | P151 | /chords/a-minor |  | piano_keyword_research_combined.xlsx｜关键词数据!A482:G482 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K1124 | all chords on piano | 260 | 同义词合并 | P148 | /chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A484:G484 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K1127 | beautiful chord progressions piano | 260 | 页面代表词 | P177 | /chord-progressions | beautiful | piano_keyword_research_combined.xlsx｜关键词数据!A487:G487 | 查询优美钢琴和弦走向；必须在该页提供实际结果，不只增加一个关键词。
K1130 | c minor in piano | 260 | 页面代表词 | P166 | /chords/c-minor |  | piano_keyword_research_combined.xlsx｜关键词数据!A488:G488 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K1132 | cb piano chord | 260 | 页面代表词 | P167 | /chords/c-flat-major |  | piano_keyword_research_combined.xlsx｜关键词数据!A489:G489 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K1133 | chords for a major | 260 | 同页补充/条件/问题（非同义） | P161 | /chords/by-key | a-major | piano_keyword_research_combined.xlsx｜关键词数据!A491:G491 | 查询A大调和弦集合；必须在该页提供实际结果，不只增加一个关键词。
K1134 | chords in key | 260 | 同义词合并 | P152 | /chords/by-key |  | piano_keyword_research_combined.xlsx｜关键词数据!A492:G492 | 有内容的调性选择器与各级和弦表；支持已有G/D/C/E/A/F及D minor任务
K1135 | chords in the key of c piano | 260 | 同义词合并 | P159 | /chords/by-key | c-major | piano_keyword_research_combined.xlsx｜关键词数据!A913:G913 | 查C大调各级和弦；必须在该页提供实际结果，不只增加一个关键词。
K1140 | full piano chord chart | 260 | 同义词合并 | P148 | /chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A494:G494 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K1143 | happy chord progressions | 260 | 页面代表词 | P178 | /chord-progressions | happy | piano_keyword_research_combined.xlsx｜关键词数据!A495:G495 | 愉快情绪和弦走向；必须在该页提供实际结果，不只增加一个关键词。
K1161 | how to make chord progressions | 260 | 同义词合并 | P237 | /chord-progressions | how-it-works | piano_keyword_research_combined.xlsx｜关键词数据!A498:G498 | 说明走向是什么，附可试弹例子。
K1163 | key and chord chart | 260 | 同义词合并 | P152 | /chords/by-key |  | piano_keyword_research_combined.xlsx｜关键词数据!A499:G499 | 有内容的调性选择器与各级和弦表；支持已有G/D/C/E/A/F及D minor任务
K1166 | keyboard chords piano | 260 | 同义词合并 | P148 | /chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A500:G500 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K1172 | major and minor chords for piano | 260 | 同义词合并 | P238 | /chords | major-vs-minor | piano_keyword_research_combined.xlsx｜关键词数据!A501:G501 | 大小和弦对比包含音图/示例和区别，不用类型筛选器代替解释。
K1173 | major chord piano | 260 | 同义词合并 | P158 | /chords | major | piano_keyword_research_combined.xlsx｜关键词数据!A502:G502 | major 选择后显示经过核对的实际和弦结果。
K1174 | major piano chord | 260 | 同义词合并 | P158 | /chords | major | piano_keyword_research_combined.xlsx｜关键词数据!A503:G503 | major 选择后显示经过核对的实际和弦结果。
K1176 | most common chord progression | 260 | 同义词合并 | P172 | /chord-progressions | common | piano_keyword_research_combined.xlsx｜关键词数据!A504:G504 | 常见和弦走向集合；必须在该页提供实际结果，不只增加一个关键词。
K1179 | name chord piano | 260 | 同义词合并 | P153 | /chords/finder |  | piano_keyword_research_combined.xlsx｜关键词数据!A505:G505 | 选择音符；列出可能命名、低音与拼写说明
K1182 | naming chords piano | 260 | 同页补充/条件/问题（非同义） | P153 | /chords/finder |  | piano_keyword_research_combined.xlsx｜关键词数据!A506:G506 | 选择音符；列出可能命名、低音与拼写说明
K1193 | piano chord chart pdf | 260 | 同页补充/条件/问题（非同义） | P148 | /chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A510:G510; Google 第2批 图10; Google 第2批 图11 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K1194 | piano chord progression | 260 | 同义词合并 | P173 | /chord-progressions |  | piano_keyword_research_combined.xlsx｜关键词数据!A511:G511 | 常见走向列表；C/E/A调转写选择；优美/愉快效果标签；含义与使用说明；打印
K1195 | piano chord shapes | 260 | 同页补充/条件/问题（非同义） | P220 | /guide/piano-chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A512:G512 | 步骤、构成、指法示意及连接练习；链接查图工具
K1196 | piano chord sheet printable | 260 | 同页补充/条件/问题（非同义） | P148 | /chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A513:G513 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K1197 | piano chord transitions | 260 | 页面代表词 | P242 | /guide/piano-chords | transitions | piano_keyword_research_combined.xlsx｜关键词数据!A514:G514 | 练习钢琴和弦连接/换和弦动作；必须在该页提供实际结果，不只增加一个关键词。
K1198 | piano chords b major | 260 | 同义词合并 | P150 | /chords/b-major |  | piano_keyword_research_combined.xlsx｜关键词数据!A515:G515 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K1199 | piano chords in the key of c | 260 | 同义词合并 | P159 | /chords/by-key | c-major | piano_keyword_research_combined.xlsx｜关键词数据!A971:G971 | 查C大调各级和弦；必须在该页提供实际结果，不只增加一个关键词。
K1200 | piano chords pdf | 260 | 同页补充/条件/问题（非同义） | P148 | /chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A516:G516 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K1212 | piano minor chords | 260 | 同义词合并 | P154 | /chords | minor | piano_keyword_research_combined.xlsx｜关键词数据!A520:G520 | minor 选择后显示经过核对的实际和弦结果。
K1225 | popular chord progression | 260 | 同义词合并 | P172 | /chord-progressions | common | piano_keyword_research_combined.xlsx｜关键词数据!A526:G526 | 常见和弦走向集合；必须在该页提供实际结果，不只增加一个关键词。
K1226 | power chords piano | 260 | 页面代表词 | P168 | /chords | power | piano_keyword_research_combined.xlsx｜关键词数据!A527:G527 | power chord 的实际结果与使用说明，不能只有标签。
K1235 | a chord inversions piano pdf |  | 同页补充/条件/问题（非同义） | P149 | /chords/a-major |  | 关键词策略构建器数据汇总.md｜L467｜piano scales > piano chords and progressions | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K1237 | a minor chord piano |  | 同义词合并 | P151 | /chords/a-minor |  | 关键词策略构建器数据汇总.md｜L463｜piano scales > piano chords and progressions | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K1240 | ab chord piano |  | 同义词合并 | P155 | /chords/a-flat-major |  | 关键词策略构建器数据汇总.md｜L75｜piano chord chart > piano chord chart | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K1241 | ab piano chord |  | 同义词合并 | P155 | /chords/a-flat-major |  | 关键词策略构建器数据汇总.md｜L462｜piano scales > piano chords and progressions | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K1266 | c chord piano |  | 同义词合并 | P163 | /chords/c-major |  | piano_keyword_research_combined.xlsx｜关键词数据!A297:G297 | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K1292 | free piano chord chart |  | 同页补充/条件/问题（非同义） | P148 | /chords |  | Google 第2批 图10 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K1293 | free piano chord chart printable pdf |  | 同页补充/条件/问题（非同义） | P148 | /chords |  | Google 第2批 图10; Google 第2批 图11 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K1298 | g chord piano |  | 页面代表词 | P169 | /chords/g-major |  | 关键词策略构建器数据汇总.md｜L163｜piano chord chart > piano scales; 关键词策略构建器数据汇总.md｜L511｜piano scales > piano scales and fingering | 当前和弦的音名/键位/音程；原位和转位；可用时播放；清晰指法说明；相关查询链接
K1307 | how many piano chords are there |  | 同页补充/条件/问题（非同义） | P148 | /chords |  | 关键词策略构建器数据汇总.md｜L77｜piano chord chart > piano chord chart; 关键词策略构建器数据汇总.md｜L321｜beginner piano sheet music > easy piano sheet music with chords | 默认有图表；根音/类型选择、试听、打印及读图说明。
K1316 | how to read a piano chord chart? |  | 页面代表词 | P247 | /chords | how-to-read | Google 第2批 图10 | 如何读键盘图、组成音和标记；深入学习连接指南。
K1323 | how to use the chord chart |  | 同页补充/条件/问题（非同义） | P247 | /chords | how-to-read | Google 第2批 图10 | 如何读键盘图、组成音和标记；深入学习连接指南。
K1328 | keyboard piano chords beginner |  | 同义词合并 | P225 | /guide/piano-chords | beginner | 关键词策略构建器数据汇总.md｜L80｜piano chord chart > piano chord chart; 关键词策略构建器数据汇总.md｜L326｜beginner piano sheet music > easy piano sheet music with chords; 关键词策略构建器数据汇总.md｜L468｜piano scales > piano chords and progressions | 初学钢琴基础和弦选择与弹法；必须在该页提供实际结果，不只增加一个关键词。
K1332 | major chords piano cheat sheet |  | 同页补充/条件/问题（非同义） | P158 | /chords | major | Google 第2批 图10 | major 选择后显示经过核对的实际和弦结果。
K1341 | pdf piano chords chart |  | 同页补充/条件/问题（非同义） | P148 | /chords |  | Google 第2批 图11 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K1345 | piano chord chart 7th |  | 页面代表词 | P170 | /chords | seventh | Google 第2批 图10; Google 第2批 图11 | 明确 7th 涉及的类别和输出；不把它无条件改成 major7。
K1346 | piano chord chart for beginners pdf |  | 同页补充/条件/问题（非同义） | P148 | /chords |  | Google 第2批 图10 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K1347 | piano chord chart jazz |  | 页面代表词 | P171 | /chords | jazz | Google 第2批 图11 | jazz 相关和弦的实际示例及说明，不只加一个风格按钮。
K1348 | piano chord chart with finger position pdf |  | 同页补充/条件/问题（非同义） | P148 | /chords |  | Google 第2批 图10; Google 第2批 图11 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K1349 | piano chord progressions pdf |  | 同页补充/条件/问题（非同义） | P173 | /chord-progressions |  | 关键词策略构建器数据汇总.md｜L109｜piano chord chart > piano chord accompaniment | 常见走向列表；C/E/A调转写选择；优美/愉快效果标签；含义与使用说明；打印
K1350 | piano chords |  | 同义词合并 | P148 | /chords |  | piano_keyword_research_combined.xlsx｜关键词数据!A309:G309; piano_keyword_research_combined.xlsx｜关键词数据!A394:G394; piano_keyword_research_combined.xlsx｜关键词数据!A434:G434; piano_keyword_research_combined.xlsx｜关键词数据!A474:G474; Google 第2批 图11 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K1351 | piano chords chart |  | 同页补充/条件/问题（非同义） | P148 | /chords |  | Google 第2批 图11 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K1352 | piano chords chart for beginners |  | 同页补充/条件/问题（非同义） | P225 | /guide/piano-chords | beginner | Google 第2批 图11 | 初学钢琴基础和弦选择与弹法；必须在该页提供实际结果，不只增加一个关键词。
K1353 | piano chords chart pdf |  | 同义词合并 | P148 | /chords |  | 关键词策略构建器数据汇总.md｜L323｜beginner piano sheet music > easy piano sheet music with chords | 默认有图表；根音/类型选择、试听、打印及读图说明。
K1354 | piano chords for beginners pdf |  | 同页补充/条件/问题（非同义） | P148 | /chords |  | Google 第2批 图11 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K1406 | pretty piano chord progressions |  | 同义词合并 | P177 | /chord-progressions | beautiful | 关键词策略构建器数据汇总.md｜L82｜piano chord chart > piano chord chart | 查询优美钢琴和弦走向；必须在该页提供实际结果，不只增加一个关键词。
K1419 | what are all the chords on piano? |  | 同页补充/条件/问题（非同义） | P148 | /chords |  | Google 第2批 图10; Google 第2批 图11 | 默认有图表；根音/类型选择、试听、打印及读图说明。
K1425 | what are the 12 chords for piano? |  | 同页补充/条件/问题（非同义） | P148 | /chords |  | Google 第2批 图10; Google 第2批 图11 | 默认有图表；根音/类型选择、试听、打印及读图说明。

## 完成任务17项
完成任务17项
证据口径：原规划来自附件；实现来自用户报告，待Codex以同一版本核对；预测数量不作强制指标。
ID | 优先级 | 阶段 | 任务 | 怎么做 | 完成标准 | 责任人 | 状态
F01 | P0 | A | 基线与任务覆盖 | 记录真实Git/route/sitemap，保留旧127快照与38任务，不重跑全部旧测试 | 158条报告路由与实际差异可解释 | Codex | not_executed
F02 | P0 | B | Extended | 9种明确子类型，理论式＋实际排列，2套视图 | 108对象语义和输入输出一致 | Codex | not_executed
F03 | P0 | C | Altered | 8种显式变音，generic alt返回范围解释 | 96对象，变音/省略/拼写负例通过 | Codex | not_executed
F04 | P0 | B | 原power缺口与常见结构补齐 | 84对象同页嵌入已有关联入口 | 无额外详情URL，power允许2音类及根音重复 | Codex | not_executed
F05 | P0 | D | Hub全库查阅 | 默认25轻卡，所有supported对象可按根音与类型找到 | 可以从首页Chords找到C13/C7b9/Cdim7，而非只有目录 | Codex | not_executed
F06 | P0 | D | Finder | 音符输入＋可选实际低音；精确、已定义省略、多解释分开 | 等音/对称/重复/斜杠/不支持输入不误导 | Codex | not_executed
F07 | P1 | D | By-key | 24个大调与自然小调，三音＋七和弦表 | 336行真实结果；和弦root不同于key；小调变化明确 | Codex | not_executed
F08 | P1 | D | Progressions | 8套进行×12调，loop/速度/当前音与共同音 | 96例；情绪仅主观标签；无真实演奏评分 | Codex | not_executed
F09 | P0 | E | Guide学习路径 | 从三和弦→转位→七和弦→省略→进行，真实例子 | 原beginner/transitions保留，新增知识不删除原正确正文 | Codex | not_executed
F10 | P0 | E | 练习判定 | formula_pitch_classes、example_midi_set、example_pitch_classes分别命名 | 无音区误判和省略语义混淆 | Codex | not_executed
F11 | P0 | F | 打印和资产 | 保留旧145详情PDF/SVG；当前例子打印；专题材料生成 | 生成资产不冒充人工打印；文件/图/音/定义一致 | Codex | not_executed
F12 | P0 | F | 无障碍 | 焦点、触控、错误/结果朗读、文字缩放、动效偏好 | 键盘可完整操作；手动读屏检查另记录 | Codex | not_executed
F13 | P1 | F | SEO | 保持旧URL；原191词追溯；每类意图owner；rawHTML及内链 | 只2新增；不使用meta keywords；不制造参数URL | Codex | not_executed
F14 | P1 | F | 产品信任 | 来源/规则派生/作者/审阅状态与范围说明 | 无虚假教师/首创/全覆盖承诺 | Codex | not_executed
F15 | P1 | F | 事件与本地便利 | 复用当前分析器，白名单事件；可选最近使用 | 无PII/重复埋点，无analytics权限照常可用 | Codex | not_executed
F16 | P0 | G | 真实环境与发布 | 同一构建人工抽检及部署权限 | 检查结果、未测项、版本不混 | owner_and_real_testers | not_executed
F17 | P1 | H | 真实使用验证 | 目标用户任务观察与7/28/56天数据 | 不把曝光等于任务成功，不保证排名 | owner_and_real_testers | not_executed